## 05_Release_Readiness_Matrix
Release_File | Release_Label | Release_Date | Environment | Release_Status | DB_Changes | Platform_Branch | CHP_Items_In_Release | Req_Backlog_Coverage_% | Open_Gaps | Readiness_Score | Go_No_Go
21-May26-20260522113104.csv | 21-May26 | 2026-05-21 | Stage | Good |  |  | 1 | 0.1 | None | 100 | GO
20-May26-20260522113100.csv | 20-May26 | 2026-05-20 | Stage | Good |  |  | 1 | 0.1 | None | 100 | GO
15-May26-20260522113056.csv | 15-May26 | 2026-05-15 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
14-May26-20260522113052.csv | 14-May26 | 2026-05-14 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
13-May26-20260522113048.csv | 13-May26 | 2026-05-13 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
12-May26-20260522113043.csv | 12-May26 | 2026-05-12 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
08-May-26-20260522113035.csv | 08-May-26 | 2026-05-08 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
07-May-26-20260522113031.csv | 07-May-26 | 2026-05-07 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
05-May-26-20260522113027.csv | 05-May-26 | 2026-05-05 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
04-May26-20260522113023.csv | 04-May26 | 2026-05-04 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
30-April26-20260522113019.csv | 30-April26 | 2026-04-30 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
29-April26-20260522113014.csv | 29-April26 | 2026-04-29 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
28-April26-20260522113006.csv | 28-April26 | 2026-04-28 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
27-April26-hotfix-20260522112957.csv | 27-April26-hotfix | 2026-04-27 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
27-April26-hotfix_2-20260522113001.csv | 27-April26-hotfix_2 | 2026-04-27 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
24-April26-hotfix-20260522112953.csv | 24-April26-hotfix | 2026-04-24 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
23-April26-20260522112949.csv | 23-April26 | 2026-04-23 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
22-April26-hotfix-20260522112937.csv | 22-April26-hotfix | 2026-04-22 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
22-April26-hotfix2-20260522112943.csv | 22-April26-hotfix2 | 2026-04-22 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
21-April26-20260522112930.csv | 21-April26 | 2026-04-21 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
21-April26-hotfix-20260522112934.csv | 21-April26-hotfix | 2026-04-21 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
20-Apr26-hotfix-20260522112926.csv | 20-Apr26-hotfix | 2026-04-20 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
17-Apr26-20260522112922.csv | 17-Apr26 | 2026-04-17 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
16-Apr26-hotfix-20260522112917.csv | 16-Apr26-hotfix | 2026-04-16 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
15-Apr26-20260522112910.csv | 15-Apr26 | 2026-04-15 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
15-Apr26-hotfix-20260522112914.csv | 15-Apr26-hotfix | 2026-04-15 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
14-Apr26-20260522112905.csv | 14-Apr26 | 2026-04-14 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
13-Apr26-20260522112900.csv | 13-Apr26 | 2026-04-13 | Stage | good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
10-April26-20260522112856.csv | 10-April26 | 2026-04-10 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
09-April26-20260522112852.csv | 09-April26 | 2026-04-09 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
07-April26-20260522112847.csv | 07-April26 | 2026-04-07 | Stage | Prod release owner: |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
03-April26-02-20260522112839.csv | 03-April26-02 | 2026-04-03 | Stage | Prod release owner: |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
03-April26-02-20260522112843.csv | 03-April26-02 | 2026-04-03 | Stage | Prod release owner: |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
02-April26-20260522112829.csv | 02-April26 | 2026-04-02 | Stage | Prod release owner: |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
01-April26-20260522112825.csv | 01-April26 | 2026-04-01 | Stage | Prod release owner: |  |  | 2 | 0.1 | None | 100 | GO
31-March2026-20260522112817.csv | 31-March2026 | 2026-03-31 | Stage | Prod release owner: |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
31-March2026-hotfix-20260522112821.csv | 31-March2026-hotfix | 2026-03-31 | Stage | Prod release owner: |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
29-March26-20260522112808.csv | 29-March26 | 2026-03-29 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
26-March26-20260522112803.csv | 26-March26 | 2026-03-26 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
24-March26-20260522112758.csv | 24-March26 | 2026-03-24 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
23-March26-20260522112753.csv | 23-March26 | 2026-03-23 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
20-March26-hotfix-20260522112747.csv | 20-March26-hotfix | 2026-03-20 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
18-March26-02-20260522112743.csv | 18-March26-02 | 2026-03-18 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
18-March26-20260522112738.csv | 18-March26 | 2026-03-18 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
17-March26-20260522112730.csv | 17-March26 | 2026-03-17 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
17-March26_02-20260522112734.csv | 17-March26_02 | 2026-03-17 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
11-March26-20260522112726.csv | 11-March26 | 2026-03-11 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
27-Feb26-20260522112720.csv | 27-Feb26 | 2026-02-27 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
26-Feb26-20260522112716.csv | 26-Feb26 | 2026-02-26 | Stage | Good |  |  | 8 | 0.5 | None | 100 | GO
24-Feb26-20260522112704.csv | 24-Feb26 | 2026-02-24 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
24-Feb26-20260522112710.csv | 24-Feb26 | 2026-02-24 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
20-Feb26-20260522112658.csv | 20-Feb26 | 2026-02-20 | Stage | Good |  |  | 4 | 0.2 | None | 100 | GO
16-Feb26-20260522112653.csv | 16-Feb26 | 2026-02-16 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
12-Feb26-20260522112648.csv | 12-Feb26 | 2026-02-12 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
5-Feb26-20260522112642.csv | 5-Feb26 | 2026-02-05 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
3-Feb26-hotfix-20260522112636.csv | 3-Feb26-hotfix | 2026-02-03 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
2-Feb26-20260522112632.csv | 2-Feb26 | 2026-02-02 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
30-Jan26-20260522112627.csv | 30-Jan26 | 2026-01-30 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
29-Jan26-20260522112622.csv | 29-Jan26 | 2026-01-29 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
27-Jan26-20260522112613.csv | 27-Jan26 | 2026-01-27 | Stage | Good |  |  | 5 | 0.3 | None | 100 | GO
24-Jan26-20260522112618.csv | 24-Jan26 | 2026-01-24 | Stage | Good |  |  | 28 | 1.7 | None | 100 | GO
12-Jan26-20260522112602.csv | 12-Jan26 | 2026-01-12 | Stage | Good |  |  | 17 | 1 | None | 100 | GO
09-Jan26-hotfix-20260522112549.csv | 09-Jan26-hotfix | 2026-01-09 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
05-Jan26-20260522112519.csv | 05-Jan26 | 2026-01-05 | Stage | Good |  |  | 9 | 0.5 | None | 100 | GO
05-Jan26-20260522112557.csv | 05-Jan26 | 2026-01-05 | Stage | Good |  |  | 9 | 0.5 | None | 100 | GO
23-Dec25-hotfix-20260522143523.csv | 23-Dec25-hotfix | 2025-12-23 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
12-Dec25-20260522143516.csv | 12-Dec25 | 2025-12-12 | Stage | Good |  |  | 26 | 1.5 | None | 100 | GO
8-Dec25 Release-20260522143509.csv | 8-Dec25 Release | 2025-12-08 | Stage | Good |  |  | 19 | 1.1 | None | 100 | GO
3-Dec25-hotfix-20260522143457.csv | 3-Dec25-hotfix | 2025-12-03 | Stage | Good |  |  | 2 | 0.1 | None | 80 | GO
02-Dec25-hotfix-20260522143451.csv | 02-Dec25-hotfix | 2025-12-02 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
28-Nov25-20260522143443.csv | 28-Nov25 | 2025-11-28 | Stage | Good |  |  | 9 | 0.5 | None | 100 | GO
25-Nov25-20260522143436.csv | 25-Nov25 | 2025-11-25 | Stage | Good |  |  | 7 | 0.4 | None | 100 | GO
6 Nov25-hotfix-20260522143355.csv | 6 Nov25-hotfix | 2025-11-06 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
5 Nov25-20260522143348.csv | 5 Nov25 | 2025-11-05 | Stage | Good |  |  | 11 | 0.7 | None | 100 | GO
31 Oct25-hotfix-20260522143342.csv | 31 Oct25-hotfix | 2025-10-31 | Stage | Good |  |  | 12 | 0.7 | None | 80 | GO
29 Oct25-hotfix-20260522143336.csv | 29 Oct25-hotfix | 2025-10-29 | Stage | Good |  |  | 2 | 0.1 | None | 80 | GO
28 Oct25-hotfix-20260522143330.csv | 28 Oct25-hotfix | 2025-10-28 | Stage | Good - Conditional sign-off |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
27-Oct25(Sales Release)-20260522143322.csv | 27-Oct25(Sales Release) | 2025-10-27 | Stage | Good |  |  | 19 | 1.1 | None | 100 | GO
15 Oct25-hotfix-20260522143242.csv | 15 Oct25-hotfix | 2025-10-15 | Stage | Good |  |  | 2 | 0.1 | None | 80 | GO
10 Oct25-20260522143236.csv | 10 Oct25 | 2025-10-10 | Stage | Good |  |  | 8 | 0.5 | None | 100 | GO
10 Oct25-hotfix-20260522143248.csv | 10 Oct25-hotfix | 2025-10-10 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
30-Sep25-hotfix-20260522143229.csv | 30-Sep25-hotfix | 2025-09-30 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
24-Sep25-hotfix-20260522143223.csv | 24-Sep25-hotfix | 2025-09-24 | Stage | Good |  |  | 3 | 0.2 | None | 80 | GO
23-Sep25-hotfix-20260522143140.csv | 23-Sep25-hotfix | 2025-09-23 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
16-Sep25-hotfix-20260522143125.csv | 16-Sep25-hotfix | 2025-09-16 | Stage | Good |  |  | 13 | 0.8 | None | 80 | GO
12-Sep25-hotfix-20260522143116.csv | 12-Sep25-hotfix | 2025-09-12 | Stage | Good |  |  | 4 | 0.2 | None | 80 | GO
10-Sep25-20260522143133.csv | 10-Sep25 | 2025-09-10 | Stage | Good |  |  | 42 | 2.5 | None | 100 | GO
03-Sep25-hotifx-20260522143106.csv | 03-Sep25-hotifx | 2025-09-03 | Stage | good |  |  | 2 | 0.1 | None | 100 | GO
25-Aug25-hotfix-20260522143058.csv | 25-Aug25-hotfix | 2025-08-25 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
22-Aug25-20260522143052.csv | 22-Aug25 | 2025-08-22 | Stage | Good |  |  | 75 | 4.4 | None | 100 | GO
13-Aug25-hotfix-20260522143044.csv | 13-Aug25-hotfix | 2025-08-13 | Stage | Good |  |  | 5 | 0.3 | None | 80 | GO
06-Aug25-hotfix-20260522143036.csv | 06-Aug25-hotfix | 2025-08-06 | Stage | Good |  |  | 9 | 0.5 | None | 80 | GO
01-Aug25-hotfix-20260522143031.csv | 01-Aug25-hotfix | 2025-08-01 | Stage | Good |  |  | 4 | 0.2 | None | 80 | GO
29-July25-hotfix-20260522143025.csv | 29-July25-hotfix | 2025-07-29 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
25-July25(data migration)-20260522143020.csv | 25-July25(data migration) | 2025-07-25 | Stage | Good |  |  | 50 | 3 | None | 100 | GO
14-July25-hotfix-20260522143014.csv | 14-July25-hotfix | 2025-07-14 | Stage | Good |  |  | 3 | 0.2 | None | 80 | GO
08-July25-hotfix-20260522143008.csv | 08-July25-hotfix | 2025-07-08 | Stage | Good |  |  | 8 | 0.5 | None | 80 | GO
02-July25-hotfix-20260522143002.csv | 02-July25-hotfix | 2025-07-02 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
26-Jun25-20260522142957.csv | 26-Jun25 | 2025-06-26 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
19-Jun25-hotfix-20260522142947.csv | 19-Jun25-hotfix | 2025-06-19 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
11-Apr25-20260522142938.csv | 11-Apr25 | 2025-04-11 | Stage | Prod release owner: |  |  | 2 | 0.1 | None | 100 | GO
07-Apr25-20260522142924.csv | 07-Apr25 | 2025-04-07 | Stage | Good |  |  | 6 | 0.4 | None | 100 | GO
07-Apr25-hotfix-20260522142930.csv | 07-Apr25-hotfix | 2025-04-07 | Stage | Good |  |  | 1 | 0.1 | None | 80 | GO
01-Apr25-hotfix-20260522142918.csv | 01-Apr25-hotfix | 2025-04-01 | Stage | Good |  |  | 3 | 0.2 | None | 80 | GO
13-Mar25-20260522141847.csv | 13-Mar25 | 2025-03-13 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
28-Feb25-20260522141841.csv | 28-Feb25 | 2025-02-28 | Stage | Good |  |  | 6 | 0.4 | None | 100 | GO
24-Feb25-20260522141836.csv | 24-Feb25 | 2025-02-24 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
19-Feb25-hotfix-20260522141830.csv | 19-Feb25-hotfix | 2025-02-19 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
12-Feb25-20260522141824.csv | 12-Feb25 | 2025-02-12 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
06-feb25-20260522141818.csv | 06-feb25 | 2025-02-06 | Stage | Good |  |  | 2 | 0.1 | None | 100 | GO
31-Jan25-hotfix-20260522141807.csv | 31-Jan25-hotfix | 2025-01-31 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
28-Jan25-hotfix-20260522141812.csv | 28-Jan25-hotfix | 2025-01-28 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
22-Jan25-20260522141757.csv | 22-Jan25 | 2025-01-22 | Stage | Good |  |  | 5 | 0.3 | None | 100 | GO
10-Jan25-20260522141751.csv | 10-Jan25 | 2025-01-10 | Stage | Good |  |  | 14 | 0.8 | None | 100 | GO
08-Jan25-20260522141744.csv | 08-Jan25 | 2025-01-08 | Stage | Good |  |  | 8 | 0.5 | None | 100 | GO
31-Dec24-20260522141739.csv | 31-Dec24 | 2024-12-31 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
20-Dec24-20260522141733.csv | 20-Dec24 | 2024-12-20 | Stage | Good |  |  | 1 | 0.1 | None | 100 | GO
18-Dec24-hotfix-20260522141725.csv | 18-Dec24-hotfix | 2024-12-18 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
17-Dec24-20260522141717.csv | 17-Dec24 | 2024-12-17 | Stage | Good |  |  | 21 | 1.2 | None | 100 | GO
11-Dec24-hotfix-20260522141712.csv | 11-Dec24-hotfix | 2024-12-11 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
05-Dec24-20260522141700.csv | 05-Dec24 | 2024-12-05 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
05-Dec24-hotfix-20260522141705.csv | 05-Dec24-hotfix | 2024-12-05 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
02-Dec24-20260522141654.csv | 02-Dec24 | 2024-12-02 | Stage | Good |  |  | 7 | 0.4 | None | 100 | GO
28-Nov24-hotfix-20260522141647.csv | 28-Nov24-hotfix | 2024-11-28 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
26-Nov24-hotfix-20260522141642.csv | 26-Nov24-hotfix | 2024-11-26 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
22-Nov24-20260522141636.csv | 22-Nov24 | 2024-11-22 | Stage | Good |  |  | 12 | 0.7 | None | 100 | GO
20-Nov24-hotfix-20260522141624.csv | 20-Nov24-hotfix | 2024-11-20 | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL
19-Nov24-hotifx-20260522141615.csv | 19-Nov24-hotifx | 2024-11-19 | Stage | Good |  |  | 2 | 0.1 | None | 100 | GO
18-Nov24-20260522141606.csv | 18-Nov24 | 2024-11-18 | Stage |  |  |  | 0 | 0 | Missing release status; No CHP traceability in release notes | 70 | CONDITIONAL
12th Nov Release-20260522143409.csv | 12th Nov Release |  | Stage | Good |  |  | 26 | 1.5 | None | 100 | GO
19th Nov Release-20260522143421.csv | 19th Nov Release |  | Stage | Good |  |  | 9 | 0.5 | None | 100 | GO
13th Nov Release(Purchase Release)-20260522143415.csv | 13th Nov Release(Purchase Release) |  | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
30- March2026-20260522112812.csv | 30- March2026 |  | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
7th Nov Release-20260522143400.csv | 7th Nov Release |  | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
QE Release Notes 2026-20260522112607.csv | QE Release Notes 2026 |  | Stage | Prod release owner: |  |  | 0 | 0 | No CHP traceability in release notes | 85 | CONDITIONAL
19th Nov-hotfix-20260522143429.csv | 19th Nov-hotfix |  | Stage | Good |  |  | 0 | 0 | No CHP traceability in release notes | 65 | CONDITIONAL